## Infrastructure
LALA HARYDAL PARK — INFRASTRUCTURE
Category export · AI Drone Survey · DDA / DTU parameter framework
Site: Lala Harydal Park, North Delhi (DDA)
Survey date: 19 May 2026, 11:49-12:12 IST (single-date baseline)
Category: Infrastructure
CATEGORY SCORE
Indicator | Mean | Min | Max | Rating
Infrastructure | 76.3% | 29.6% | 90% | Good
SCENE COVERAGE (park-wide mean)
Metric | Mean | Min | Max
Paved area | 0% | 0% | 0%
DETECTOR FINDINGS
Detector class | Records | Mean cond. % | Worst % | Condition
Walking Track | 178 | 54.7 | 29.6 | Poor
Kerb / Edging | 1092 | 84.8 | 73.1 | Good
Bench | 282 | 80.5 | 70.4 | Good
Open Gym Equipment | 331 | 79.3 | 58.7 | Good
Pathway Obstruction | 0 | — | — | Not observed in these clips
Paved Area | 100 | 78 | 72 | Good
Excavation / Disturbed Ground | 0 | — | — | Not observed in these clips
Material Stockpile | 0 | — | — | Not observed in these clips
Construction Activity | 0 | — | — | Not observed in these clips
ANOMALIES (worst first)
Priority | Zone | Anomaly | Severity | Cond. % | Suggested action
10 | Palm avenue & lawns | Walking Track | High | 33.1 | Resurface / patch the track; restore edge definition and camber.
53 | Formal beds & pathways | Walking Track | High | 42.2 | Resurface / patch the track; restore edge definition and camber.
227 | Formal beds & pathways | Walking Track | Medium | 52.7 | Resurface / patch the track; restore edge definition and camber.
327 | Formal beds & pathways | Walking Track | Medium | 59.8 | Resurface / patch the track; restore edge definition and camber.
RECOMMENDED ACTIONS
# | Priority | Finding | Recommended action | Owner
6 | Low | Tree tree cover, topiary, kerbs, benches and paved avenues are all in reasonable condition. | Maintain the current regime for planting and hardscape; the investment needed is in the ground plane. | Horticulture Division
7 | Process | Items recorded on site with no detector class yet: flower beds, weeds near pathways, water pipes and leakage, dustbins, gates, gazebo, signposts, streetlights, parking, boundary wall and railings as distinct classes. | Confirm which matter most for the DDA report and they can be added. Flower beds and weeds-near-pathways are both straightforward and directly relevant to this park. | Survey / Drone Cell
8 | Process | The saturated-colour rule reports 681 play-equipment and 331 gym-equipment records in a park where none was observed - it is catching red benches and planter edging. | Treat those two rows as unverified. A scene-level gate similar to the one used for construction can suppress them per park on request. | Survey / Drone Cell
Generated from Lala_Hardeval_AI_Detection_Report.xlsx · DDA AI Park Monitor. Figures are the park-wide mean across 3 analysed clips, recomputed directly from the detection log rather than the workbook's own summary formulas.