## Infrastructure
SANJAY LAKE — INFRASTRUCTURE
Category export · AI Drone Survey · DDA / DTU parameter framework
Site: Sanjay Lake, East Delhi (DDA)
Survey date: 19 May 2026 (single-date baseline survey)
Category: Infrastructure
CATEGORY SCORE
Indicator | Mean | Min | Max | Rating
Infrastructure | 77.1% | 37.4% | 96.2% | Good
SCENE COVERAGE (park-wide mean)
Metric | Mean | Min | Max
Paved area | 6.3% | 0% | 27.3%
DETECTOR FINDINGS
Detector class | Records | Mean cond. % | Worst % | Condition
Walking Track | 556 | 50.6 | 32.3 | Poor
Kerb / Edging | 1368 | 81.9 | 73.2 | Good
Bench | 511 | 79.4 | 69.3 | Good
Open Gym Equipment | 1418 | 87.1 | 69.5 | Good
Pathway Obstruction | 0 | — | — | Not observed in these clips
Paved Area | 301 | 56.9 | 47.3 | Poor
Excavation / Disturbed Ground | 0 | — | — | Not observed in these clips
Material Stockpile | 0 | — | — | Not observed in these clips
Construction Activity | 0 | — | — | Not observed in these clips
ANOMALIES (worst first)
Priority | Zone | Anomaly | Severity | Cond. % | Suggested action
22 | Children's play area | Walking Track | High | 33.5 | Resurface / patch the track; restore edge definition and camber.
24 | Children's play area | Walking Track | High | 33.8 | Resurface / patch the track; restore edge definition and camber.
35 | Children's play area | Walking Track | High | 35.8 | Resurface / patch the track; restore edge definition and camber.
42 | Children's play area | Walking Track | High | 36.5 | Resurface / patch the track; restore edge definition and camber.
64 | Children's play area | Walking Track | High | 39.6 | Resurface / patch the track; restore edge definition and camber.
78 | Children's play area | Walking Track | High | 41 | Resurface / patch the track; restore edge definition and camber.
86 | Children's play area | Walking Track | High | 42.6 | Resurface / patch the track; restore edge definition and camber.
88 | Children's play area | Walking Track | High | 42.7 | Resurface / patch the track; restore edge definition and camber.
93 | Children's play area | Walking Track | High | 43.3 | Resurface / patch the track; restore edge definition and camber.
104 | Children's play area | Walking Track | High | 44.3 | Resurface / patch the track; restore edge definition and camber.
110 | Children's play area | Walking Track | Medium | 45.3 | Resurface / patch the track; restore edge definition and camber.
113 | Children's play area | Walking Track | Medium | 45.5 | Resurface / patch the track; restore edge definition and camber.
125 | Children's play area | Walking Track | Medium | 47.1 | Resurface / patch the track; restore edge definition and camber.
130 | Children's play area | Walking Track | Medium | 47.5 | Resurface / patch the track; restore edge definition and camber.
147 | Children's play area | Walking Track | Medium | 48.5 | Resurface / patch the track; restore edge definition and camber.
153 | Children's play area | Paved Area | Medium | 49.3 | Patch spalled or cracked paving; re-lay settled bays.
154 | Children's play area | Walking Track | Medium | 49.4 | Resurface / patch the track; restore edge definition and camber.
157 | Children's play area | Walking Track | Medium | 49.7 | Resurface / patch the track; restore edge definition and camber.
159 | Children's play area | Walking Track | Medium | 49.9 | Resurface / patch the track; restore edge definition and camber.
163 | Children's play area | Walking Track | Medium | 50.1 | Resurface / patch the track; restore edge definition and camber.
227 | Children's play area | Paved Area | Medium | 53.3 | Patch spalled or cracked paving; re-lay settled bays.
275 | Children's play area | Walking Track | Medium | 56.8 | Resurface / patch the track; restore edge definition and camber.
288 | Children's play area | Paved Area | Medium | 58.9 | Patch spalled or cracked paving; re-lay settled bays.
292 | Children's play area | Walking Track | Medium | 59.4 | Resurface / patch the track; restore edge definition and camber.
RECOMMENDED ACTIONS
# | Priority | Finding | Recommended action | Owner
5 | Medium | Play and gym equipment is broadly serviceable, but several units score materially below their cluster mean on the paint-integrity index. | Inspect the lowest-scoring units listed in '7. Anomalies'; sand, prime and repaint, and check all fixings, bearings and footings. | Engineering / Works
6 | Medium | Kerb and edging runs show breaks in continuity, and some walking-track segments score poorly on surface uniformity. | Reset displaced kerb stones and patch or resurface the affected track segments. | Engineering / Works
Generated from Sanjay_Lake_Park_AI_Detection_Report.xlsx · DDA AI Park Monitor. Figures are the park-wide mean across 1 analysed clip, recomputed directly from the detection log rather than the workbook's own summary formulas.