## Infrastructure
SMRITI VAN MAYUR VIHAR — INFRASTRUCTURE
Category export · AI Drone Survey · DDA / DTU parameter framework
Site: Smriti Van Mayur Vihar, Mayur Vihar (DDA)
Survey date: 19 May 2026, 16:54-17:35 IST (single-date baseline)
Category: Infrastructure
CATEGORY SCORE
Indicator | Mean | Min | Max | Rating
Infrastructure | 75.9% | 49.8% | 92.4% | Good
SCENE COVERAGE (park-wide mean)
Metric | Mean | Min | Max
Paved area | 0% | 0% | 0%
DETECTOR FINDINGS
Detector class | Records | Mean cond. % | Worst % | Condition
Walking Track | 335 | 52.9 | 34.4 | Poor
Kerb / Edging | 991 | 83.1 | 73.6 | Good
Bench | 178 | 75.4 | 68.1 | Good
Open Gym Equipment | 195 | 81.9 | 64.9 | Good
Pathway Obstruction | 1 | 44.1 | 44.1 | Poor
Paved Area | 42 | 75.3 | 72.6 | Good
Excavation / Disturbed Ground | 1 | 48.1 | 48.1 | Poor
Material Stockpile | 0 | — | — | Not observed in these clips
Construction Activity | 2 | 32.1 | 19.8 | Critical
ANOMALIES (worst first)
Priority | Zone | Anomaly | Severity | Cond. % | Suggested action
6 | Children's play area | Construction Activity | Critical | 19.9 | Confirm the works are sanctioned and that a site-safety plan, hoarding and signage are in place. Record against the sanctioned works schedule for contractor verification.
26 | Children's play area | Walking Track | High | 37.1 | Resurface and reinstate the track after the works.
39 | Children's play area | Walking Track | High | 40.1 | Resurface and reinstate the track after the works.
41 | Children's play area | Walking Track | High | 40.6 | Resurface and reinstate the track after the works.
58 | Children's play area | Pathway Obstruction | High | 44.1 | Clear the walking track immediately and provide a signed, barricaded pedestrian diversion.
60 | Children's play area | Walking Track | High | 44.4 | Resurface and reinstate the track after the works.
63 | Waterlogged ground | Construction Activity | High | 44.6 | Confirm the works are sanctioned and that a site-safety plan, hoarding and signage are in place. Record against the sanctioned works schedule for contractor verification.
90 | Children's play area | Excavation / Disturbed Ground | Medium | 48.2 | Barricade and signpost the excavation; reinstate and compact the surface once works are done.
97 | Children's play area | Walking Track | Medium | 48.5 | Resurface and reinstate the track after the works.
109 | Waterlogged ground | Walking Track | Medium | 49.3 | Resurface and reinstate the track after the works.
126 | Children's play area | Walking Track | Medium | 50.4 | Resurface and reinstate the track after the works.
130 | Lawns & tree belt | Walking Track | Medium | 50.5 | Resurface and reinstate the track after the works.
131 | Children's play area | Walking Track | Medium | 50.6 | Resurface and reinstate the track after the works.
148 | Children's play area | Walking Track | Medium | 52.4 | Resurface and reinstate the track after the works.
157 | Children's play area | Walking Track | Medium | 53.7 | Resurface and reinstate the track after the works.
171 | Waterlogged ground | Walking Track | Medium | 54.5 | Resurface and reinstate the track after the works.
174 | Children's play area | Walking Track | Medium | 54.7 | Resurface and reinstate the track after the works.
198 | Children's play area | Walking Track | Medium | 57.2 | Resurface and reinstate the track after the works.
204 | Waterlogged ground | Walking Track | Medium | 57.7 | Resurface and reinstate the track after the works.
RECOMMENDED ACTIONS
# | Priority | Finding | Recommended action | Owner
4 | High | A piece of children's play equipment appears collapsed on the ground in the play-area clip, and the sand surface beneath the equipment is bare and hard-packed. | Inspect and make safe immediately - remove or reinstate the fallen unit, and replace the impact-absorbing surface under all play equipment. | Engineering / Works
6 | Medium | Pathways and kerb runs show wear consistent with the site record of unmaintained pavement. | Patch and resurface the worst track segments; reset displaced kerb and edging. | Engineering / Works
8 | Process | Several items recorded on site have no detector class yet: leaking water pipes, weeds near pathways, gazebo, signpost, street lamp, main gate, monuments, dead trees. | Confirm which of these matter most for the DDA report and they can be added - most are feasible; the pipe in Clip 1 is a clear, high-contrast target. | Survey / Drone Cell
Generated from Smriti_Van_AI_Detection_Report.xlsx · DDA AI Park Monitor. Figures are the park-wide mean across 4 analysed clips, recomputed directly from the detection log rather than the workbook's own summary formulas.