## Infrastructure
VASANT VATIKA — INFRASTRUCTURE
Category export · AI Drone Survey · DDA / DTU parameter framework
Site: Vasant Vatika, Vasant Kunj (DDA)
Survey date: 18 May 2026, 16:05-16:08 IST (single-date baseline)
Category: Infrastructure
CATEGORY SCORE
Indicator | Mean | Min | Max | Rating
Infrastructure | 76.7% | 50.9% | 90% | Good
SCENE COVERAGE (park-wide mean)
Metric | Mean | Min | Max
Paved area | 0% | 0% | 0%
DETECTOR FINDINGS
Detector class | Records | Mean cond. % | Worst % | Condition
Walking Track | 401 | 56.7 | 39.9 | Poor
Kerb / Edging | 1301 | 85 | 74.2 | Good
Bench | 324 | 79.1 | 67.7 | Good
Open Gym Equipment | 288 | 81.3 | 66.7 | Good
Pathway Obstruction | 0 | — | — | Not observed in these clips
Paved Area | 45 | 81.6 | 71.2 | Good
Excavation / Disturbed Ground | 0 | — | — | Not observed in these clips
Material Stockpile | 0 | — | — | Not observed in these clips
Construction Activity | 0 | — | — | Not observed in these clips
ANOMALIES (worst first)
Priority | Zone | Anomaly | Severity | Cond. % | Suggested action
45 | Open gym & hedge beds | Walking Track | High | 43.6 | Resurface / patch the track; restore edge definition and camber.
51 | Open gym & hedge beds | Walking Track | Medium | 45.4 | Resurface / patch the track; restore edge definition and camber.
52 | Open gym & hedge beds | Walking Track | Medium | 46 | Resurface / patch the track; restore edge definition and camber.
78 | Fountain & formal garden | Walking Track | Medium | 51.1 | Resurface / patch the track; restore edge definition and camber.
100 | Central lawn & avenue | Walking Track | Medium | 52.8 | Resurface / patch the track; restore edge definition and camber.
103 | Open gym & hedge beds | Walking Track | Medium | 52.9 | Resurface / patch the track; restore edge definition and camber.
118 | Open gym & hedge beds | Walking Track | Medium | 54.7 | Resurface / patch the track; restore edge definition and camber.
125 | Open gym & hedge beds | Walking Track | Medium | 55.2 | Resurface / patch the track; restore edge definition and camber.
135 | Open gym & hedge beds | Walking Track | Medium | 55.9 | Resurface / patch the track; restore edge definition and camber.
137 | Open gym & hedge beds | Walking Track | Medium | 56.5 | Resurface / patch the track; restore edge definition and camber.
140 | Open gym & hedge beds | Walking Track | Medium | 56.9 | Resurface / patch the track; restore edge definition and camber.
147 | Open gym & hedge beds | Walking Track | Medium | 58.5 | Resurface / patch the track; restore edge definition and camber.
RECOMMENDED ACTIONS
# | Priority | Finding | Recommended action | Owner
3 | Medium | The site record notes getting worse paint on the gym equipment. The equipment was detected and scored on paint integrity. | Inspect the lowest paint-integrity scorers in the anomaly register; sand, prime and repaint, and check fixings and footings. | Engineering / Works
7 | Process | No class exists for: gazebo, streetlight, dustbin, water pipes, boundary wall distinct from kerb, or dead trees as a class separate from dry plant growth. | Confirm which matter most for the DDA report and they can be added. | Survey / Drone Cell
Generated from Vasant_Vatika_AI_Detection_Report.xlsx · DDA AI Park Monitor. Figures are the park-wide mean across 3 analysed clips, recomputed directly from the detection log rather than the workbook's own summary formulas.